## Project Planner
Group 2 Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 4 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Read Textbook | 2 | 12 | 2 | 10 | 100%
Plan Querries | 1 | 7 | 1 | 7 | 100%
Meeting 1 | 6 | 1 | 6 | 1 | 100%
Repo Creation | 7 | 1 | 7 | 1 | 100%
To Do List | 3 | 11 | 8 | 7 | 100%
Meeting 2 | 11 | 1 | 11 | 1 | 100%
Error Checks in Querry | 10 | 3 | 11 | 3 | 100%
Analyze in Pairs/ Group Video | 12 | 1 | 12 | 1 | 100%
Brightspace submission | 13 | 1 | 13 | 1 | 100%
NACE | 11 | 2 | 11 | 2 | 100%
[6 empty] | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21