## Group member 1
To-do list
To be completed by: |  | Shiwlee/Izaz |  | Homework 4 & 5
Deadline: |  | 2025-10-09 |  | Date 10/10/2025
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Textbook | 2025-09-28 | 2025-10-04 | 2025-10-06 | 7 days | Go over sub querries & cte with groupmates
100% | Plan Querries | 2025-09-28 | 2025-10-04 | 2025-10-06 | 7days | issue with cte. Solve before deadline
100% | Meeting 1 | 2025-10-03 | 2025-10-03 | N/A | 1 day | remind group leader of tasks due
100% | Repo Creation | 2025-10-04 | 2025-10-04 | N/A | 0.5 days | completed
100% | To Do List | 2025-09-30 | 2025-10-05 | 2025-10-10 | 11 days | completed
100% | Meeting 2 | 2025-10-08 | 2025-10-09 | N/A | 2 days | Prep for group video discussion. Account for emergency delays
100% | Error Check in Querry | 2025-10-07 | 2025-10-09 | 2025-10-10 | 3 days | make sure comments exist for every line of code
100% | Hand-off | 2025-10-09 | 2025-10-09 | N/A | 1 day | Final group video
100% | Follow-up | 2025-10-10 | 2025-10-10 | N/A | 1 day | Check repo has all required files. Brightspace submission

## Group member 2
To-do list
To be completed by: |  | Azmain/Christopher/Haiyan |  | Chapter 4 & 5
Deadline: |  | 2025-10-10 |  | 2025-10-10
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Textbook | 2025-09-28 | 2025-10-04 | 2025-10-06 | 7 days | Go over sub querries & cte with groupmates
100% | Plan Querries | 2025-09-28 | 2025-10-04 | 2025-10-06 | 7days | issue with cte. Solve before deadline
100% | Meeting 1 | 2025-10-03 | 2025-10-03 | N/A | 1 day | remind group leader of tasks due
100% | Repo Creation | 2025-10-04 | 2025-10-04 | N/A | 0.5 days | completed
100% | To Do List | 2025-09-30 | 2025-10-05 | 2025-10-10 | 11 days | completed
100% | Meeting 2 | 2025-10-08 | 2025-10-09 | N/A | 2 days | Prep for group video discussion. Account for emergency delays
100% | Error Check in Querry | 2025-10-07 | 2025-10-09 | 2025-10-10 | 3 days | make sure comments exist for every line of code
100% | Hand-off | 2025-10-09 | 2025-10-09 | N/A | 1 day | Final group video
100% | Follow-up | 2025-10-10 | 2025-10-10 | N/A | 1 day | Check repo has all required files. Brightspace submission

## Group member 3
To-do list
To be completed by: |  | Zarin/Eusan |  | Chapter 4 & 5
Deadline: |  | 2025-10-10 |  | Date 10/102025
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Textbook | 2025-09-28 | 2025-10-04 | 2025-10-06 | 7 days | Go over sub querries & cte with groupmates
100% | Plan Querries | 2025-09-28 | 2025-10-04 | 2025-10-06 | 7days | issue with cte. Solve before deadline
100% | Meeting 1 | 2025-10-03 | 2025-10-03 | N/A | 1 day | remind group leader of tasks due
100% | Repo Creation | 2025-10-04 | 2025-10-04 | N/A | 0.5 days | completed
100% | To Do List | 2025-09-30 | 2025-10-05 | 2025-10-10 | 11 days | completed
100% | Meeting 2 | 2025-10-08 | 2025-10-09 | N/A | 2 days | Prep for group video discussion. Account for emergency delays
100% | Error Check in Querry | 2025-10-07 | 2025-10-09 | 2025-10-10 | 3 days | make sure comments exist for every line of code
100% | Hand-off | 2025-10-09 | 2025-10-09 | N/A | 1 day | Final group video
100% | Follow-up | 2025-10-10 | 2025-10-10 | N/A | 1 day | Check repo has all required files. Brightspace submission

## Group member 4 (hidden)
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 5 (hidden)
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6 (hidden)
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up